# NE ATLANTIC MARINE BIOLOGICAL AQC SCHEME COMMITTEE MEETING

Agenda 21st July 2026 1400-1600

Venue: Teams Online

Confirmed Attendees: David Johns (DJ, MBA, Chair), Claire Mason (CM, CEFAS, PSA Technical Manager), Claire Taylor (CT, MBA Technical Secretary), Jim Ellis (JE, CEFAS, Fish Technical Manager), Tim Mackie (TM, DAERA, Senior Scientific Officer), David Hall (DH, APEM Benthic Administrator), Ross Griffin (RG, Contractors Rep, Ocean Ecology), Martina Brunetta (MB, MBA, Zooplankton Technical Manager), Margarita Fernandez (MF, IRTA, Phytoplankton Technical Manager), Lydia McIntyre-Brown (LMB, APEM Ltd, PSA administrator), Kris Carrigan (KC, JNCC, Epibiota Technical Manager), Kate Wade (KW,JNCC,  eDNA Technical Manager), Soren Pears (SP, APEM, Macroalgal administrator), Debbie Walsh (DW, APEM, Fish Administrator), Paul McIllwaine (PM, CEFAS, Marine Benthic Ecologist), Russell McCune (RM, AFBI) and Tom Tangye (TT, NRW, Specialist Advisor),

Apologies: Graham Phillips (GP, EA, Finance Manager), Matt Green (MG,NRW, Marine Monitoring Ecologist), Gillian Annett (GA, DAERA, Macroalgal |Technical Manager), Vera Fonseca (VR, Cefas, eDNA Technical Manager) and Gina Brackenreed Johnston (GBJ, APEM, Macroalgae administrator).

| - Last Meetings Actions (summarised below on the agenda) |  | ALL |
| --- | --- | --- |
| - Minutes of the last meeting |  | CT |
| Approval of April meeting minutes |  | DJ |
| - Epibiota update |  | KC |
| - Phytoplankton update |  | MF |
| - Priorities to HBDSEG |  | DJ |
| - PSA update |  | CM/LMB |
| - Benthic Invertebrates update |  | DH |
| - Macroalgae update |  | GA/GBJ |
| - Fish update |  | JE/DW |
| - Zooplankton update |  | MB |
| - eDNA update |  | KW/VF |
| - AOB |  | ALL |
| - Contractor Questions |  | RG/MR |
| - Finance update* Confidential |  | GP |

- Ongoing actions:

Ongoing:

eDNA:

Ongoing Action: few lines to be added to Under Development section of website but needs expanding,. Update: VR to send something to CT. Action: CT to chase along with an update. Update has been received, CT to create a paragraph or two but to check with Kate first. Further update – Kate to provide CT with some text next week.

General:

Look at developing a LinkedIn page – conscious of the effort involved to update. Formed part of the discussion around advertising the scheme and broadening the participation.  TT advised in the chat if there is an ambition to grow and promote the NMBAQC scheme, establishing a LinkedIn page should be an important part of that strategy.

Phytoplankton

Action: MF to send CT a list of participants to update on the website. To also see if it’s possible to see the change in participants from different regions over the years. Action: MF to send update to CT

PSA

The committee also discussed how to raise our profile, CM advised she did add a slide about us at the  workshop. Action: CT to check mailchimp distribution lists to see if recent participants from all components are included, we can only do this though with the individuals permission. Update – CT it’s as up to date as can be and I will also ask people from any inquiries if they would like to be added. CT to check all lists and also add in contact from BGS (update – done).

Benthic Invertebrates

With some assistance from Tim Worsfold, I have updated the Benthic Invertebrate/Workshops section of the website.  Tim has some photos we could include of the workshops but I’m not sure if this is something we can do in terms of GDPR? (CT) The committee advised this is only possible if authorisation has been sought.  We have to be very careful of third parties asking for licences of images. Action: CT to feedback to TW - done.

AOB

Next Meeting with be in July time (online)  with a face to face meeting to be arranged in October –  discussions were held regarding location and RG offered Bristol. Previously Cardiff (MG) has been used, both these locations are fairly straightforward for the majority of the committee.  Action: All let CT know if you would be willing to host – Both Ross and Dave Hall have offered use of their facilities.  Thank you. Action: CT to arrange doodle poll for potential visit in Bristol, hosted by RG for October.

- Minutes of the last meeting (DJ):  approved

- Epibiota update (KC/KW):

April 2026:

The NMBAQC operational and interpretation guidelines have been shared with Big Picture and NMBAQC members for peer review. All comments are to be returned by May. Edits will be completed and documents published later in FY2627. New chapters will be determined by the Big Picture Group and drafted for selection by November 27, with the aim to deliver 1st drafts by March 27 for wider review.

Funding for Big Picture Group has not yet been confirmed for FY2627. Proposed plans have been submitted to Defra's Marine and Fisheries R&D fund.  A 4 year delivery of the Big Picture network has been submitted.

The main objectives over the next 4 years are:

  - Making UK Marine Imagery AI Annotation-Ready

  - Standardised Annotation Guidance for UK Marine Organisms

  - QA/QC Guidance for Marine Imagery Analysis

  - Improving Imagery workflows

  - Future-Proofing Training, Standardisation and QA

Details of each objective are to be finalised with full project delivery plan for year 1 scoped out once funding confirmed.

July 2026:

Coordination of The Big Picture Group funding was confirmed in June. JNCC will continue to act as coordinator and secretariat, funded by Defra through their Marine and Fisheries R&D fund.

The NMBAQC Epibiota Guidelines update continues. Final comments have been received after a peer review organised through The Big Picture Group. These comments are being integrated and the aim is to publish both the operational and interpretation guidelines later this year. The review has identified some gaps in the guidelines. These gaps will be addressed over the coming years with new chapters commissioned as appropriate.

A project addressing the need for QA/QC guidance for marine imagery analysis has begun this year and will continue into next year. This year a workshop will be held to review existing QA/QC approaches and agree a route forward. A scoping paper outlining the way(s) forward will follow and a protocol and workflow will be developed with a view to conducting pilot tests in FY 2728.

The framework developed will:

  - Provides clear, consistent and transparent analytical approaches applicable across survey types (e.g. habitat mapping, MPA verification).

  - Define acceptable limits of analytical variation to support decision-making robustness.

  - Support legal defensibility and confidence in imagery-derived evidence.

  - Establish a foundation for AI and machine learning applications.

The UK Morphotaxa Classification System project is continuing. This work aims to provide a standardised classification system for use with seabed imagery that can be applied to UK shelf sea taxa and North Atlantic deep-sea taxa.

Kate advised the group of a SMarTaR-ID (Standardised marine taxon reference imaged database) project which is an online catalogue of images, quality checked by taxonomists. Further information can be found on their website   Home - SMarTaR-ID

The committee were also given a link to another initiative FathomVerse | Ocean Science Community

For any further information on these projects please contact TheBigPicture@jncc.gov.uk

Kris Carrigan advised the committee Kate will be taking over the role of Technical Manager for Epibiota and he is moving to a new position.  The committee thanked him for his work and wished him well.

- Phytoplankton update (MF):

Margarita provided the committee with a verbal update.  Samples for the IPI exercise were sent out on the 1/06/2026 and all have been received although there have been problems encountered at Australian customs (concerning the samples in seawater).  Extensions have been given to those participants who’s samples were delayed (original deadline 1/09/26).  125 participants have signed up to the exercise and results will be distributed by the end of November.

- Priorities to HBDSEG (DJ):

The last HBDSEG meeting was a couple of weeks ago.  DJ reinforced what NMBAQC was and stood for.  Myle’s retirement was announced and DJ asked all groups to think about Myle’s replacement as Benthic Invertebrates Technical Manager.  The group thanked Myles for his contribution over many years.

Claire Mason asked about Blue Carbon work.  Action: CM to send DJ the proposal and DJ to chat to Roger Proudfoot.

The next HBDSEG meeting is in person and scheduled for the end of October 2026. Any items will need raising through DJ the week before. Action: CT to ask the committee nearer the time.

- PSA update (CM/LMB):

PARTICLE SIZE COMPONENT PROGRESS REPORT

2025-26, Year 32

  - Subscriptions (to date)

| LabCode | PS 96/97 | PS98/ 99 | PS – OS34/35/36 |
| --- | --- | --- | --- |
| PSA_3201 | 1 | 1 | - |
| PSA_3202 | 1 | 1 | - |
| PSA_3203 | 1 | 1 | 1 |
| PSA_3204 | 1 | 1 | - |
| PSA_3205 | 1 | 1 | - |
| PSA_3206 | 1 | 1 | - |
| PSA_3207 | 1 | 1 | - |
| PSA_3208 | 1 | 1 | 1 |
| PSA _3209 | 1 | 1 | 1 |
| PSA _3210 | 1 | 1 | 7 |
| PSA _3211 | 1 | 1 | - |
| PSA _3212 | 1 | 1 | 1 |
| PSA _3213 | 1 | 1 | 1 |
| PSA _3214 | 1 | 1 | 1 |
| PSA _3215 | 1 | 1 | 1 |
| PSA _3216 | 1 | 1 | 1 |
| PSA _3217 | 1 | 1 | - |
| PSA_3218 | - | - | 1 |
| PSA_3219 | - | - | 1 |
| ° (change from 2024/25) | 17 (±0) | 16 (-1) | - (+6) |

6.2 2025-2026, Year 32 Operations

Particle Size exercises have been distributed in line with the 2025-2026 timetable (available below). There was an amendment to the timetable which meant PS98 and PS99 were distributed later than originally planned, participants were emailed to inform them of this change and presented with an updated timetable. Returns, results and exercise status details are summarised in the table below.

PSA_3219 and PSA_3218 pulled out of the own-sample module and PSA_3211 have pulled out of the PS module for PS98 & PS99.

| Exercise | Status | Returns / Comments |
| --- | --- | --- |
| PS96 | Samples distributed 31/10/25 Submission deadline 12/12/25 Interim reports issued 12/01/26 Final Report to be issued 30/03/26 Exercise in progress | Sands Test 14 out of 17 returned results |
| PS97 | Samples distributed 31/10/25 Submission deadline 12/12/25 Interim reports to be issued 12/01/26 Final Report to be issued 30/03/26 Exercise in progress | Mixed Test 14 out of 17 returned results |
| PS98 | Samples distributed 20/02/26 Submission deadline 17/04/26 Interim reports to be issued 01/05/26 Final Report to be issued 29/05/26 Exercise in progress | Fines Test 14 out of 16 returned results |
| PS999 | Samples to be distributed 20/02/26 Submission deadline 17/04/26 Interim reports issued 11/05/26 Final Report to be issued 29/05/26 Exercise in progress | Mixed Test 14 out of 16 returned results |
| OS34-36 | Data submission deadline Batch 1 28/11/25 Batch 2 27/03/26 Sample submission deadline Batch 1 12/12/25/ Batch 2 01/05/26 OS Module Summary Report deadline Batch 1 27/03/26/ Batch 2 03/07/26 Exercises on-going | 14 out of 15 data sets submitted 42 out of 45 samples selected 42 out of 45 samples received 4 out of 15 reports sent |
| 2025/26 Annual Report & SoPs | Annual Report & Statement of Performance documents deadline 30/07/26* | Report template drafted. |
| Workshop | Lowestoft (potentially) | Summer 2026 |

PS96 & PS97 – fourteen of the seventeen participants submitted results. Two asked for an extension and are still yet to submit data and one lab did not reply to any correspondence.

PS98 &PS99 – 14 out of 16 results returned at time of writing. Two labs did not submit results or reply to any correspondence.

PS-OS 34 – 36 Batch 1 – 4 participants submitted data in Batch 1, all AQC has now been completed with all reports sent to the participant.

PS-OS 34 – 36 Batch 2 – all participants bar one have submitted data and samples; AQC complete; reports in progress.

Annual report and PS-OS Batch 2 reporting deadlines have shifted slightly to the end of July and end of August respectively.

Claire Mason held an online workshop to discuss the findings of the extra laser RT (spiked with micro plastics), results of this will feed into the PSA workshop planned for summer 2026.

*LmB advised the committee that the 2025/2026 SoPs have been pushed back until the end of August.

Particle Size Component 2025-2026 Timetable (Scheme Year 32)

| Module / Exercise | Event | Date |
| --- | --- | --- |
| PS96 & PS97 | Samples distributed | 31/10/25 |
|  | Results deadline | 12/12/25 |
|  | Interim reporting deadline | 19/12/25 |
|  | Final report deadline | 30/03/2026 |
| PS98 & PS99 | Samples distributed | 20/02/26 |
|  | Results deadline | 17/04/26 |
|  | Interim reporting deadline | 01/05/26 |
|  | Final report deadline | 29/05/26 |
| PS-OS 34 - 36 | Request for sample data distributed | 31/10/25 |
| Batch 1 | Data submission deadline for sample selection | 28/11/25 |
|  | Selected samples submission deadline | 12/12/25 |
|  | Interim report final deadline (for samples received before 14 Feb 2025) | 27/03/26 |
| Batch 2 | Data submission deadline for sample selection | 27/03/26 |
|  | Selected samples submission deadline | 01/05/26 |
|  | Interim report final deadline | 30/07/26 |
| Annual Report | Annual report deadline | 28/08/26 |
| Workshop –Results of laser test + methodology training | Lowestoft (potentially) | Summer 2026 |

- Benthic Invertebrates update (DH):

BENTHIC INVERTEBRATE COMPONENT PROGRESS REPORT

2025-26, Year 32

  - Subscriptions

| LabCode | RT69/70 | LR30 | OS89/90/91 |
| --- | --- | --- | --- |
| BI_3201 | 1 | 1 | - |
| BI_3202 | 1 | - | 1 |
| BI_3203 | 1 | - | - |
| BI_3204 | 1 | - | 1 |
| BI_3205 | 1 | 1 | - |
| BI_3206 | 1 | - | - |
| BI_3207 | 1 | - | - |
| BI_3208 | 1 | - | - |
| BI_3209 | 1 | - | 1 |
| BI_3210 | 1 | - | - |
| BI_3211 | 1 | - | 1 |
| BI_3212 | 1 | - | - |
| BI_3213 | 1 | - | - |
| BI_3214 | 1 | - | 1 |
| BI_3215 | 1 | - | 1 |
| BI_3216 | 1 | - | 1 |
| BI_3217 | 1 | 1 | 1 |
| BI_3218 | 1 | 1 | 1 |
| BI_3219 | 1 | - | - |
| BI_3220 | 1 | - | - |
| BI_3226 | - | - | 1 |
| BI_3227 | - | - | 1 |
| BI_3228 | - | - | 1 |
| BI_3229 | - | - | 1 |
| BI_3230 | - | - | 1 - |
| BI_3231 | - | - | 1 |
| BI_3232 | - | - | 1 |
| BI_3233 | - | - | 1 |
| BI_3234 | - | - | 1 |
| BI_3235 | - | - | 1 |
| BI_3236 | - | - | 1 |
| BI_3237 | - | - | 1 |
| BI_3238 | - | - | 1 |
| BI_3239 | - | - | 1 |
| BI_3240 | - | - | 1 |
| BI_3241 | - | - | 1 |
| BI_3242 | - | - | 1 |
| BI_3243 | - | - | 1 |
| ° (change from 2024/25) | 20 (-3) | 4 (-1) | 27 26 (+6) |

7.2 2025-2026, Year 32 Operations

Benthic Invertebrate exercises have been distributed in line with the 2025-2026 timetable (available below). Returns, results and exercise status details are summarised in the table below.

| Exercise | Status | Returns / Comments |
| --- | --- | --- |
| RT69 | Specimens distributed 31/10/25 Submission deadline 12/12/25 Interim reports issued 19/12/25 Ring Test Bulletin issued 20/02/26 Exercise complete | General Ring Test 17 (from 16 labs) out of 20 data sets received |
| RT70 | Specimens distributed 20/02/26 Submission deadline 17/04/26 Interim reports to be issued 01/05/26 Ring Test Bulletin issued 15/07/26 Exercise complete | Targeted Ring Test – Sessile Fauna 16 (from 15 labs) out of 20 data sets received 1 lab did not participate due to relocation |
| LR30 | Request for specimens to be distributed 31/10/25 Submission deadline 12/12/25 Interim reports deadline 13/03/26 LR Module Summary Report to be issued 27/03/26 (extended) Exercise in progress | 2 of the 4 sets of specimens received 2 sets reported 1 set awaited |
| OS89-91 | Sample data requested 31/10/25 Data submission deadline Batch 2 27/03/26 Sample submission deadline Batch 2 01/05/26 (extended) OS Module Summary Report deadline 03/07/26 Module in progress | 24 out of 26 data sets received All 72 requested samples received 56 samples reported to date, including 3 samples via the external auditor |
| 2025/26 Annual Report & SoPs | Annual Report & Statement of Performance documents deadline 31/07/26* In progress | Draft report on-going SoP template created |

*DH advised this deadline might need extending by a week.

  - Issues arising

Ring Test (RT) Schedule Adjusted

The final bulletin for RT70 was delayed for additional taxonomic input and Committee review/signoff (many thanks to Paul McIlwaine & Tim Mackie for their quick responses).

Laboratory Reference (LR) & Own Sample (OS) Batch 2 Schedules Adjusted

Reminders and extension have been granted to enable maximum returns for this year’s LR & OS exercises.

  - Taxonomic Workshops

Taxonomic Workshop for Beginners, APEM Ltd, Letchworth, 2-6 November 2026

Taxonomic workshop for beginners ‘call for expression of interest’ has been circulated for provisional dates w/c 2 November 2026 at APEM’s Letchworth laboratory.

So far there have been 5/6 responses, the workshop will go ahead for new staff members.

  - Forthcoming 2026-2027, Year 33 Operations

Benthic Invertebrate exercises are to be distributed in line with the provisional 2026-2027 timetable (available below).

Invertebrate Component 2025-2026 Timetable (Scheme Year 32)

| Module / Exercise | Event | Date |
| --- | --- | --- |
| RT69 - General | Samples distributed | 31/10/25 |
|  | Results deadline | 12/12/25 |
|  | Interim reporting deadline | 19/12/25 |
|  | Final report deadline | 20/02/26 |
| RT70 - Targeted | Samples distributed | 20/02/26 |
|  | Results deadline | 17/04/26 |
|  | Interim reporting deadline | 01/05/26 |
|  | Final report deadline | 29/05/26 |
| LR30 | Protocol and request for specimens distributed | 31/10/25 |
|  | Specimen submission deadline | 12/12/25 |
|  | Interim reports deadline | 13/03/26 |
|  | LR summary report deadline | 27/03/26 |
| OS89–91 | Request for sample data distributed | 31/10/25 |
| Batch 1 | Data submission deadline for sample selection | 28/11/25 |
|  | Selected samples submission deadline | 12/12/25 |
|  | Interim report final deadline (for samples received before 12 December 2025) | 27/03/26 |
| Batch 2 | Data submission deadline for sample selection | 27/03/26 |
|  | Selected samples submission deadline | 01/05/26 |
|  | Interim report final deadline | 03/07/26 |
|  | OS summary report deadline | 24/07/26 |
| Annual Report | Annual report deadline | 31/07/26 |
| Workshop – beginners | APEM Ltd, Letchworth Laboratory | w/c 24/11/25 |
| Workshop – experts | Venue TBC – subject to demand | *TBC (Autumn 2026) |

Invertebrate Component 2026-2027 Timetable (Scheme Year 33)

| Module / Exercise | Event | Date |
| --- | --- | --- |
| RT71 - General | Samples distributed | 02/10/26 |
|  | Results deadline | 27/11/26 |
|  | Interim reporting deadline | 04/12/26 |
|  | Final report deadline | 15/01/27 |
| RT72 - Targeted | Samples distributed | 05/02/27 |
|  | Results deadline | 02/04/27 |
|  | Interim reporting deadline | 09/04/27 |
|  | Final report deadline | 07/05/27 |
| LR31 | Protocol and request for specimens distributed | 02/10/26 |
|  | Specimen submission deadline | 11/12/26 |
|  | Interim reports deadline | 12/03/27 |
|  | LR summary report deadline | 26/03/27 |
| OS92–94 | Request for sample data distributed | 02/10/26 |
| Batch 1 | Data submission deadline for sample selection | 27/11/26 |
|  | Selected samples submission deadline | 11/12/26 |
|  | Interim report final deadline (for samples received before 11 December 2026) | 26/03/27 |
| Batch 2 | Data submission deadline for sample selection | 26/03/27 |
|  | Selected samples submission deadline | 07/05/27 |
|  | Interim report final deadline | 02/07/27 |
|  | OS summary report deadline | 23/07/27 |
| Annual Report | Annual report deadline | 30/07/27 |
| Taxonomic Workshop – beginners | APEM Ltd, Letchworth Laboratory – subject to demand | w/c 02/11/26 |
| Taxonomic Workshop – experts | Venue TBC – subject to demand | TBC |

V1_July2026

- Macroalgae update (GA/GBJ/SP):

MACROALGAE BIOMASS AND PERCENTAGE COVER COMPONENT PROGRESS REPORT

2025-26, Year 32

  - Subscriptions

| Lab Code | RT17 OMC | RT17 OMB |
| --- | --- | --- |
| MA_3001 | 1 | - |
| MA_3002 | 1 | - |
| MA_3003 | 1 | 1 |
| MA_3004 | 1 | 1 |
| MA_3005 | 1 | 1 |
| MA_3006 | 1 | 1 |
| MA_3007 | 1 | 1 |
| MA_3008 | 1 | 1 |
| MA_3009 | 1 | 1 |
| MA_3010 | 1 | 1 |
| Total (change from last year) | 10 (0) | 8 (-2) |

Government participants: EA, AFBI, DAERA, NRW

Private participants: None

8.2 .   2025-2026, Year 32 Operations

All circulations of MA exercises will be distributed in line with the 2025-2026 timetable (available below). Returns are summarised in the table below.

| Exercise | Status | Returns / Comments |
| --- | --- | --- |
| RT17 OMC | Samples distributed: 27/01/2026 |  |
|  | Sample deadline: 14/03/2026 | 1 participant did not submit results |
|  | Interim reports issued: 10/04/2026 |  |
|  | Final reports issued: 08/05/2026 |  |
|  | Exercise complete | 9 submissions received |
| RT17 OMB | Samples distributed: 27/01/2026 |  |
|  | Sample deadline: 14/03/2026 |  |
|  | Interim reports issued: 10/04/2026 |  |
|  | Final reports issued: 08/05/2026 |  |
|  | Exercise complete | - submissions received |

  - Notes

Of the ten laboratories participating in the OMC test nine submitted results. In total twenty two individual submissions were entered from the participating laboratories.

Of the three organisations participating in the OMB test all eight participants submitted their test results.

For RT17 the methodology has been updated to use modified z-scores, derived from median values rather than standard z-scores based on mean values as has been used in previous ring tests. This is because the standard z-scores are easily skewed by one or two extreme values in smaller data sets, whereas the modified z-score has better resistance to such extreme values and is more effective at identifying outliers. Further details have been provided in the final report.

Continuing on from participant feedback the macroalgal biomass tests in RT17 comprised of mixed artificial materials.

Macroalgae Biomass and Percentage Cover Component 2025-2026 Timetable (Scheme Year 32)

| Module / Exercise | Event | Date |
| --- | --- | --- |
| RT17 OMB | Samples distributed: 27/01/2026 | 27/01/2026 |
|  | Sample deadline: 14/03/2026 | 14/03/2026 |
|  | Interim reports issued: 10/04/2026 | 09/04/2026 |
|  | Final reports issued: 08/05/2026 | 08/05/2026 |
|  | Exercise complete |  |
| RT17 OMC | Samples distributed: 27/01/2026 | 27/01/2026 |
|  | Sample deadline: 14/03/2026 | 14/03/2026 |
|  | Interim reports issued: 10/04/2026 | 09/04/2026 |
|  | Final reports issued: 08/05/2026 | 08/05/2026 |
|  | Exercise complete |  |

SP has sent CT the latest OMB/OMC ring tests and they are now on the NMBAQC website.

- Fish Update (JE/DW)

FISH COMPONENT PROGRESS REPORT (v2)

2025–2026, Year 32

  - 2025-2026, Year 32 Subscriptions

| LabCodes | F-RRT17 | F-RT19 |
| --- | --- | --- |
| F_3201 |  | 1 |
| F_3202 |  | 1 |
| F_3203 | 1 |  |
| F_3204 | 1 |  |
| F_3205 | 1 |  |
| F_3206 | 1 |  |
| F_3207 | 1 |  |
| F_3208 | 1 |  |
| F_3209 | 1 | 1 |
| F_3210 | 1 | 1 |
| F_3211 | 1 | 1 |
| F_3212 | 1 |  |
| F_3213 |  | 1 |
| F_3214 |  | 1 |
| F_3215 |  | 1 |
| F_3216 |  | 1 |
| F_3217 |  | 1 |
| F_3218 |  | 1 |
| F_3219 |  | 1 |
| F_3220 |  | 1 |
| F_3221 |  | 1 |
| F_3222 |  | 1 |
| Total (change from last year) | 10 (-3) | 15 (+1) |

  - 2025–2026, Year 32 Operations

Interim and final results sent to participants for both exercises. Reports ready to be sent for review but awaiting two submissions from each exercise.

Participant from Italy advised that no courier is authorised to transport dead animals despite all the correct paperwork and labelling being in place. Suggested APEM request the import through TNT. This could be tried with a small package to test if it makes it through before attempting to send the larger package containing the specimens. This would have an added cost, to be discussed.

| Module / Exercise | Status | Returns | Date |
| --- | --- | --- | --- |
| F-RRT17 | Protocol and request for specimens distributed (including supply of fish postage boxes) | 10 test boxes circulated | 17/11/25 |
|  | Specimen submission deadline | 9 out of 10 submissions received | *12/01/26 |
|  | Interim reporting deadline | Completed for submitted participants | 17/03/26 |
|  | Final report deadline | In progress | TBC |
| F-RT19 | Samples (specimens & images) distributed | Specimens distributed to 15 participants | 19/01/26 |
|  | Results deadline | 12 out of 15 submissions received | *20/03/26 |
|  | Interim reporting deadline | Pending | 13/03/26* |
|  | Final report deadline | In progress | TBC* |
| Annual Report | Annual report deadline |  | TBC |
| Workshop – experts | TBC – subject to demand |  | TBC |
| Workshop – beginners | TBC – subject to demand |  | TBC |

  - Issues arising

Steady supply of multiple specimens of a diverse range of fish species remains an issue.  Licence conditions for some fish surveys require the return of all fish caught.  APEM Ltd. would like to extend our thanks to CEFAS (UK), Marine Institute (Ireland) and DAERA (Northern Ireland) for their help in sourcing specimens for this years’ ring test.

  - Taxonomic Workshop

Currently no taxonomic workshop is planned for fish. A targeted workshop can be developed if sufficient interest is shown.

  - Outstanding issues

N/A

Action: DJ to check with the UoP/PML to see if they have any specimens DW can have (needs around 20 per species, 15 for participants plus spares).

Action: JE to see if he can also find more. The NHM may also have some.

- Zooplankton Update (MB):

Following the discussions held during the in-person workshop, the results have now been finalised. Participants are receiving their certificates confirming their participation in the ring test and attendance at the workshop.

The results presentation and participants’ laboratory presentations have been made available to all participants.

The final report is now being prepared for upload to the NMBAQC website, marking the formal conclusion of the 2025–2026 exercise.

MB advised the committee of using the Z scores in the enumeration component as didn’t feel they were the best, gave error thresholds to negate this. MB advised there were also problems with shipping at Canadian customs.

The next ring test for zooplankton will be 2027/2028.

- eDNA (VF/KW):

April 2026

Continued funding for the coordination of the UK Marine Biomolecular Group (MBG) has not yet been confirmed. Proposed plans have been submitted to Defra's Marine and Fisheries R&D fund.

This year the UK MBG (led by JNCC and funded by Defra) progressed a number of actions/projects for which reports will be published next financial year.

The UK Marine DNA Action Plan: built on information initially gathered at the March 2025 workshop, this Action Plan identifies barriers and the actions needed to overcome them if we are to move towards using biomolecular methods operationally for marine monitoring. Some actions are relevant for the wider DNA community (cross ecosystem or media), others are specific to marine. Standardisation and guidance came out as a strong theme with high priorities associated. Going forward the UK MBG aims to lead on marine focussed actions whilst contributing to projects that are more widely applicable.

Operationalising biomolecular methods for marine monitoring: a decision-making guide for sample collection: decision trees detailing minimum and gold standard for sampling water, sediment, or bulk fauna with links to existing protocols. This is aimed at those who do not have a molecular background but are interested in including molecular methods in their field work.

July 2026:

Coordination of the UK Marine Biomolecular Group (MBG) funding was confirmed in June. This group was established in Sept 2024 by JNCC. JNCC will continue to act as coordinator and secretariat, funded by Defra through their Marine and Fisheries R&D fund.

This year (April 2026 - March 2027) projects under the Uk MBG include:

  - The first UK MBG working group has been established: Standardisation and Guidance. This group are identifying action(s) in the Action Plan to progress.

  - UK MBG Case Studies: these will be communication tools for those not familiar with molecular methods to explain what eDNA can and can't do. Aim is to increase confidence in the methods, application  and their outputs, with a marine focus. A call out for suggestions will be issues later in the summer.

  - Best practice guidelines: JNCC will lead on drafting a protocol for the use of metaprobes for marine statutory monitoring. This work will work across Government agencies to identify who is using metaprobes and for what. It will seek to agree to standardise protocols where possible.

For any further information on these projects please contact UKMBG@jncc.gov.uk

- AOB:

Action All: Please provide updates for each component 48 hrs before each committee meeting

- Contractor Questions (RG):

One item was given to RG and this was passed onto the relevant Technical Manager.

- Finance (GP) : *Confidential