## Readme
BENTHIC IMAGERY ACTION PLAN TRACKER
Version: | 1.0
Last updated: | 2020-03-27
Prepared by: | Plan Development Group of the Big Picture Benthic Imagery Analysis Workshop (March 2019)
PDG members (Mar19-Mar20): | Henk van Rein | Joint Nature Conservation Committee | Lead
| Alison Benson | Envision Mapping Ltd | Environmental consultancy representative
| Charlie Lindenbaum | Natural Resources Wales | Inshore SNCB imagery representative
| Hayley Hinchen | Joint Nature Conservation Committee | Offshore SNCB imagery representative
| Jen Durden | National Oceanography Centre | Academic research representative
| Jon Hawes | Centre for Environment, Fisheries and Aquaculture Science | Government research representative
| Phil Boulcott | Marine Scotland Science | Government research representative
About the Benthic Imagery Action Plan Tracker: The Benthic Imagery Action Plan provides a strategic framework to carry out necessary improvements to a wide range of imagery analysis standards in the UK. Under the governance of the North-East Atlantic Marine Biological Analytical Quality Control Scheme (NMBAQC) of the Healthy and Biologically Diverse Seas Evidence Group (HBDSEG), the Action Plan lays out a ‘road map’ for the UK to follow that will encompass current needs for improvement as well as those expected to emerge with increasing use of new technologies. A key purpose of the Action Plan is to streamline the improvements into coherent work flows, so that national resources are used more efficiently. There will also be greater opportunities for knowledge exchange and collaborative working via the Action Plan. This spreadsheet, the 'Action Plan Tracker', provides a means of recording progress towards tasks and as a tool to enable better planning between organisations interested in carrying out tasks from the Action Plan. A static copy is published on the NMBAQC website and a 'live' copy is maintained by the Action Plan Coordinator of the Big Picture Group.
SPREADSHEET CONTENTS:
1. Action Plan Tracker tab (APT):
| ACTION PLAN TASK INFORMATION | Theme | General working theme of the task
|  | Task no. | Unique ID of the task
|  | Task | This is a list of the tasks (projects/actions/ideas) provided by participants at the Big Picture Workshop that are required to progress benthic imagery analysis standards and working practices across the UK
|  | Proposed way of working | The likely approach need to carry out the task: Action, Coordination, Project, Multiple projects, Workshop
|  | Suggested deliverable/s | The intended result/deliverable/output from the task
|  | Priority | All tasks have a composite prioritisation score to indicate the relative importance of the task in the Action Plan. This is calculated by adding the following factors together: 1. the total number of connections each task has to others (both within its theme and outside), e.g. 8 connections; 2. the hierarchical/procedural order/level of the task within each theme, with earlier tasks appearing higher in the flowcharts and scoring more than lower tasks that would depend more on completion of the higher order tasks (scale varies across themes depending task hierarchies but max scale is 1-8), e.g. 5 levels up from bottom of theme; 3. the relative urgency and importance of task as recommended by Big Picture Workshop participants and Plan Development Group, scored on a 1-10 scale with 10 representing immediate need, e.g. task urgency score 8. When these scores are added together they are sorted into scales to represent their relative priority in this Action Plan. The composite scores, scale ranges and recommended actions are listed here:
|  |  | High priority (H) | Moderate priority (M) | Low priority (L)
|  |  | Scores >15 | Scores 10-15 | Scores 1-9
|  |  | Must be prioritised in first phase of Action Plan, for immediate action as soon as projects can be set up. Alternatively, these tasks must form the key aims of projects connected to this Action Plan | These are the majority of tasks in this Action Plan and tend to underpin the success of many of the High Priority tasks. They should be accompany the High Priority tasks in most projects but not be the focus of the project | Important tasks that are not critical to the success of the Action Plan but nonetheless represent important work areas that should be completed when they can be. Could be factored into projects to bring additional value
|  | Task status | The status of the task. Can be "Complete", "On-going", "Under consideration" or "Hasn't started"
| TASK OUTPUTS | Output link (weblink to download files) | A weblink to a site where key task outputs can be accessed and downloaded
| TASK DEVELOPMENT | Task leads (current/future interest) | Organisations that are currently leading work on this task, perhaps in a project, and/or organisations with an interest in being a lead partner in taking this task forward in future. They would be expected to organise a project team, lead project development and management, as well as seek funding for the work
|  | Task collaborators/team (current/future interest) | Organisations that are currently working within a wider team in this task area but not leading the task. This column is also for organisations to express their interest in working in a team in which they are expected to contribute to the delivery of future tasks but not to lead them
|  | Task steering group (current/future interest) | Organisations that currently review and steer progress on a task or are interested in doing so for a future task. They are not expected to work on or lead a task but rather their committment is to provide advice and guidance on how the task could be best delivered
|  | Task funding source (current/suggested) | Current or potential future funding sources for the task
|  | Project name | The name of the project in which the task is to be delivered
| ADDITIONAL TASK INFORMATION | Current work in task area | Existing relevant progress and current work in this task that could contribute to the delivery of the task
|  | Notes for task | Additional notes relevant to this task
2. Big_Picture_Group tab: lists organisations that are involved in the NMBAQC Big Picture Group
VERSION CONTROL
Version | Date | Notes | Author | Distribution
0.1 | 2019-09-13 | Initial version created using notes Big Picture workshop | Henk van Rein | To PDG
1 | 2020-03-27 | First 'live' Action Plan Tracker for NMBAQC | Henk van Rein | Big Picture Group; NMBAQC website

## APT
ACTION PLAN TASK INFORMATION | [6 empty] | TASK OUTPUTS | TASK DEVELOPMENT |  |  |  |  | ADDITIONAL TASK INFORMATION
Theme | Task no. | Task | Proposed way of working | Suggested deliverable/s | Priority | Task status | Output link (weblink to download files) | Task leads (current/future interest) | Task collaborators/team (current/future interest) | Task steering group (current/future interest) | Task funding source (current/suggested) | Project name | Current work in task area | Notes for task
Governance & co-ordination | 1 | Embed Action Plan in suitable governance structure (HBDSEG) | PDG working | HBDSEG Benthic Imagery Action Plan | H | Complete |  | JNCC | Cefas, NOC, Envision Ltd, NRW, MSS | The Big Picture Group | Defra | Defra Marine Methodologies
Governance & co-ordination | 2 | Create an Action Plan managing body and systems for coordinating projects across UK | Group coordination | HBDSEG Benthic Imagery Action Plan Coordinator | H | Under consideration |  | JNCC, NMBAQC
Governance & co-ordination | 3 | Explore range of options and decide on optimum approaches for publishing and sharing new research findings, standards and recommendations for the working group | Coordination | Recommended information sharing routes for imagery work | L | Under consideration |  | PDG; Big Picture group
Governance & co-ordination | 4 | Create working group file-sharing and collaboration site | Lead action | File-sharing and collaboration site for Big Picture Group | M | On-going |  | JNCC |  | The Big Picture Group | Defra | Defra Marine Methodologies | JNCC have been trialling a collaboration site on Microsoft Teams since July 2019. | Other options under consideration are Huddle and Slack.
Governance & co-ordination | 5 | Explore imagery cost models for standard development, research, training and data dissemination | Coordination/ Review | Options for imagery cost models for standards development | H | Hasn't started
Governance & co-ordination | 6 | Develop contract management guidelines for benthic imagery analysis work in UK | Lead action | Improved imagery analysis contract specifications | M | Hasn't started | [7 empty] | Task supported by CMA/SNCBs
Governance & co-ordination | 7 | Review imagery data culture in UK and explore possible incentives to share imagery data | Coordination/ Review | Range of options for incentives for sharing of imagery data across UK | L | Hasn't started | [7 empty] | Task supported by CMA/SNCBs
Governance & co-ordination | 8 | Discuss imagery standard requirements with Department of Business, Energy and Industrial Strategy (BEIS) | Coordination | BEIS collaboration for standard setting | L | Hasn't started
Governance & co-ordination | 9 | Identify taxonomic experts for all taxonomic groups | Group action and coordination | List of benthic taxonomic experts | M | Hasn't started | [7 empty] | The Big Picture Group could collectively create this list
Governance & co-ordination | 10 | Create image analysis training body and governance structure to manage training materials and potentially carry out a range of courses/refreshers and publicise workshops | Coordination | Imagery training body | L | Hasn't started | [7 empty] | Shouldn’t this be the NMBAQC?
Governance & co-ordination | 11 | Create a machine learning and annotation user ‘group’ for the UK | Coordination | Machine learning and imagery annotation user group | M | Hasn't started
Overarching guidelines and purposes for imagery | 12 | Identify and define range of main purposes for using benthic imagery | Project | Defined range of standard purposes for using benthic imagery | H | In progress |  | JNCC | The Big Picture Group via questionnaires and interviews | The Big Picture Group | Defra | Defra Marine Methodologies
Overarching guidelines and purposes for imagery | 13 | Identify standard requirements for grouped main purposes and create standard table and decision tree flowchart | Project | Core purposes for using benthic imagery and minimum requirements for each purpose | H | In progress |  | JNCC | The Big Picture Group via questionnaires and interviews | The Big Picture Group | Defra | Defra Marine Methodologies
Overarching guidelines and purposes for imagery | 14 | Guidance for entire imagery analysis work flow (design, analysis, randomisation, annotation, statistics), including decision tree flowchart | Action | Annotation order of imagery randomised in procedures | H | Hasn't started | [7 empty] | Should task be supported by NMBAQC and MEDIN regarding data flows and standards?
Overarching guidelines and purposes for imagery | 15 | Develop guidance on determining appropriate sampling units from imagery data sets, including aggregation criteria (e.g. randomness) to meet minimum sample size recommendations for different purposes and targets | Project | Sampling unit guidance | M | Hasn't started
Overarching guidelines and purposes for imagery | 16 | Alignment of imagery acquisition parameters with minimum sample size recommendations and sample selection criteria for each core purpose | Multiple projects | Acquisition practices aligned with sample size and selection recommendations | H | Hasn't started
Overarching guidelines and purposes for imagery | 17 | Develop minimum data standards for imagery core purposes | Multiple projects | Imagery data output standards for standard purposes | H | Hasn't started
Overarching guidelines and purposes for imagery | 18 | Develop minimum requirements for acquisition that meets the needs of each common purpose, to include assurance that minimum sample sizes are attained for each purpose | Multiple projects | Minimum acquisition standards for standard purposes | M | Hasn't started
Overarching guidelines and purposes for imagery | 19 | Develop minimum standards for data quality and apply to in-house and contracted analyses, including time and budget estimates in contract specifications | Coordination | Data quality standards for in-house and contractual analyses | H | Hasn't started
Acquisition of imagery | 20 | Develop short guidance for minimum suitable conditions for imagery acquisition on surveys | Project | Minimum suitable conditions for imagery acquisition on survey | M | Hasn't started
Acquisition of imagery | 21 | Develop 'live' methods for assessment of initial image quality while on survey | Project | Enhanced on-survey QA and QC of imagery | M | Hasn't started
Acquisition of imagery | 22 | Review capabilities, requirements and limitations of different video formats (HD-4K-8K) | Literature review and recommendations | Future capabilities of video | L | Hasn't started
Acquisition of imagery | 23 | Review use of low-cost camera systems for acquisition of benthic imagery | Literature review and recommendations | Low-cost camera system recommendations | M | Hasn't started
Acquisition of imagery | 24 | Review of laser-profiling techniques for different purposes | Literature review and recommendations | Laser profiling recommendations | L | Hasn't started
Acquisition of imagery | 25 | Review citizen science approaches for using benthic imagery and develop recommendations for future approaches | Literature review and recommendations | Citizen science recommendations | M | Hasn't started
Acquisition of imagery | 26 | Diver based methods review | Literature review and recommendations | Guidelines for diver imagery acquisition regarding wafting | M | Hasn't started |  |  |  | NRW |  |  |  | Task co-led by NRW, NE, SNH and DAERA? Could be carreid out via Marine Monitoring Group.
Acquisition of imagery | 27 | Review of ancillary equipment usage and provide recommendations on best practice | Literature review and recommendations | Best-practice recommendations on use of ancillary equipment | M | Hasn't started
Acquisition of imagery | 28 | Review of environmental data acquisition and usage, and provide recommendations on best practice | Literature review and recommendations | Best-practice recommendations on environmental data acquisition | M | Hasn't started
Acquisition of imagery | 29 | Review potential uses of photogrammetry to meet different purposes and determine requirements of imagery to be acquired – apply to case study | Literature review and recommendations | Photogrammetry recommendations | L | Hasn't started
Acquisition of imagery | 30 | Review potential uses of video mosaicing to meet different purposes and determine requirements of imagery to be acquired – apply to case study | Literature review and recommendations | Video mosaicing recommendations | L | Hasn't started
Acquisition of imagery | 31 | Periodically update existing guidance on acquisition and analysis of imagery to reflect new developments, and produce new guidelines where necessary | Group action | Periodic reviews of procedures | H | Hasn't started |  |  |  | JNCC? |  |  |  | Should JNCC have a central role to coordinate this task but it be devolved to groups most interested in their own guidelines?
Acquisition of imagery | 32 | Contact developers of imagery acquisition systems to learn about what they are developing and, potentially, influence future developments | Group action | Developer involvement in benthic imagery work | L | Hasn't started
Acquisition of imagery | 33 | Develop intercalibration tables for different data acquisition systems, where value and benefit are possible | Project | Intercalibration tables for acquisition equipment | L | Hasn't started
Imagery annotation approaches | 34 | Review taxonomic identification approaches for benthic imagery | Project | Review of identification approaches | H | Hasn't started
Imagery annotation approaches | 35 | Develop guidance on minimum sizes of organisms that should be counted, e.g. 10mm in 1m2 | Project | Minimum taxa size guidelines for enumeration | M | Hasn't started
Imagery annotation approaches | 36 | Explore whether taxonomic identification should only be carried out for certain taxa groups that an analyst is confident to annotate | Project | Taxonomic identification guidelines | M | Hasn't started
Imagery annotation approaches | 37 | Develop Epifauna Identification Protocol (EIP) to improve consistency of taxonomic nomenclature | Project | Epifauna Identification Protocol | H | On-going |  | JNCC |  | NMBAQC
Imagery annotation approaches | 38 | Review morphological classification systems and recommend optimum approaches for future | Project | Review of morphological classification systems | H | Hasn't started
Imagery annotation approaches | 39 | Create standardised UK-based morphology-based system (e.g. CATAMI) for use on benthic imagery, including biotope monitoring | Project | Morphology-based classification system for epifauna in UK | H | Under consideration |  | Cefas? University of Plymouth? | JNCC |  |  |  |  | Should this task be lead by Cefas?
Imagery annotation approaches | 40 | Carry out pilot test to explore combined use of morphology-based classification system (e.g. CATAMI) and Epifauna Identification Protocol (EIP) | Project | Taxonomic and morphological identification guidelines | M | Hasn't started
Imagery annotation approaches | 41 | Explore possibility of using a staged approach to object identification to improve efficiency and data quality | Project | Taxonomic and morphological identification guidelines | M | Hasn't started
Imagery annotation approaches | 42 | Consider development of standard checklists of taxa/morpho-groups for surveys | Project | Reduced taxa/morpho-groups lists for surveys | M | Hasn't started
Imagery annotation approaches | 43 | Recommend minimum requirements for taxonomic and morphological identification to meet different benthic imagery purposes | Multiple projects | Minimum identification guidelines for standard purposes | M | Hasn't started
Imagery annotation approaches | 44 | Review enumeration approaches, including SACFOR, for benthic imagery | Project | Enumeration method review | H | Under consideration |  | JNCC
Imagery annotation approaches | 45 | Publish JNCC enumeration comparison method study | Project | Enumeration method comparison report | H | Complete | https://hub.jncc.gov.uk/assets/3dbf346b-685c-4db1-90a1-b205af482146 | JNCC | ASML, Envision Ltd | JNCC | Defra | Defra Marine Methodologies
Imagery annotation approaches | 46 | Explore ways to improve the consistency of records made by enumeration techniques | Project | Consistency recommendations | H | Hasn't started
Imagery annotation approaches | 47 | Decide on future uses of SACFOR | Action | SACFOR recommendations | M | Under consideration |  | Eastern IFCA? | Eastern IFCA?
Imagery annotation approaches | 48 | Develop the minimum requirements for enumeration approaches to suit different benthic imagery purposes | Multiple projects | Minimum enumeration guidelines for standard purposes | M | Hasn't started
Imagery annotation approaches | 49 | Create a decision-tree to support selection of enumeration approaches for different purposes and resourcing scenarios | Project | Minimum enumeration guidelines flowchart for standard purposes | L | Hasn't started
Imagery annotation approaches | 50 | Assessment of data metrics (accuracy, precision, consistency, efficiency) from different image annotation strategies (software vs traditional), to include aspects of working on large collections of imagery | Project | Optimisation of annotation software approaches vs traditional approaches | M | Hasn't started
Image annotation software and machine learning | 51 | Explore potential addition of metadata tags to imagery, including taxonomic and morphological classification, location, depth, temperature | Project | Addition of metadata tags to imagery | H | Hasn't started
Image annotation software and machine learning | 52 | Define features that software platforms must have for annotation and machine learning | Project | Requirements of annotation and machine learning platforms | H | Hasn't started
Image annotation software and machine learning | 53 | Implement recording of annotation metadata, i.e. analysis methods, annotation approach, analysts, training level, accreditation, analyst variability | Action | Annotation metadata recorded in procedures | H | Hasn't started |  |  |  |  | NMBAQC? MEDIN?
Image annotation software and machine learning | 54 | Integrate recommended enumeration and identification approaches with image annotation software | Action | Optimum identification and enumeration approaches used with annotation software (Milestone moment) | H | Hasn't started |  |  |  | All |  |  |  | This task should be adopted by all imagery users wherever possible
Image annotation software and machine learning | 55 | Define data format specifications necessary for machine learning algorithms to work, as well as export formats for biologists to use (e.g. csv files) | Project | Data format requirements for machine learning algorithms | H | Hasn't started
Image annotation software and machine learning | 56 | Review image annotation software and machine learning approaches for benthic imagery analysis purposes to explore differences in user interface, open-source vs contracted, point vs polygon/boxes, stills vs video | Project | Review of current annotation and machine learning approaches | H | Hasn't started
Image annotation software and machine learning | 57 | Create a pathway for annotated imagery to be shared with machine learning community (via common image library?) | Project | Open access to imagery library (for machine learning algorithms) | H | Under consideration |  | JNCC
Image annotation software and machine learning | 58 | Carry out a machine learning workshop for key participants in UK machine learning community (biologists and computer engineers) to conceptualise works flows for benthic biology imagery and facilitate collaboration | Workshop | Machine learning workshop for benthic ecologists | M | Hasn't started | [7 empty] | Should a contract be let to cover quite a few of these machine learning elements - bit of a lit review and organise a workshop?
Image annotation software and machine learning | 59 | Scope out international expertise in machine learning and explore options for how to collaborate | Coordination | List of international contacts with expertise in machine learning using benthic imagery | M | Hasn't started
Image annotation software and machine learning | 60 | Define targets/tasks for machine learning algorithms to be tested on, such as identifying indicator taxa in benthic imagery | Project | List of targets/tasks for machine learning algorithms | H | Hasn't started
Image annotation software and machine learning | 61 | Explore potential uses and value of image annotation and machine learning approaches to support Quality Assurance procedures, training, development of reference collections | Project | Role of annotation and machine learning approaches in QA | M | Hasn't started
Image annotation software and machine learning | 62 | Explore use of google imagery to substitute machine learning needs | Project | Use of google images for machine learning applications | M | Hasn't started
Image annotation software and machine learning | 63 | Develop confidence assessment approaches for machine learning outputs | Project | Machine learning confidence assessments | L | Hasn't started
Data flows | 64 | Consider what data should be shared and how it could be archived | Project | Data archive flows | M | Hasn't started
Data flows | 65 | Identify current data-sharing flows and gaps for benthic imagery | Project | Understanding current data-sharing flows and gaps | M | Hasn't started
Data flows | 66 | Target data-sharing gaps for imagery, explore potential data-sharing options products and recommend routes for organisations to follow in order to make their data available | Project | Options and recommendations to address data sharing gaps | M | Hasn't started
Data flows | 67 | Develop online common image library/catalogue to collate and share reference collections across the UK | Project | Benthic imagery library | H | Under consideration |  | University of Plymouth? | BODC? DASSH? JNCC?
Data flows | 68 | Explore options for ownership/management of central/common image library of reference collection and, potentially, other annotated imagery | Coordination | Range of options for implementation of Benthic imagery library | M | Hasn't started
Data flows | 69 | Develop confidence assessment approach for image library reference collections | Project | Image library confidence assessments | L | Hasn't started
Data flows | 70 | Identify knowledge gaps in reference collections and address | Project | Complete reference collections | L | Hasn't started
Training and Quality Assurance | 71 | Explore creation of a ‘Centre of Excellence for Taxonomy’ in the UK | Coordination | UK Centre of Excellence for Benthic Taxonomy | M | Hasn't started
Training and Quality Assurance | 72 | Develop online imagery identification tool of similar quality to Habitas.org | Project | Online identification tool | M | Hasn't started
Training and Quality Assurance | 73 | Identify and review training providers across NW Atlantic area and for different levels of taxonomic expertise/taxa groups | Coordination | List of training providers | L | Hasn't started |  |  |  | Big Picture Group |  |  |  | The Big Picture Group could collectively create this list
Training and Quality Assurance | 74 | Assess the effect training has on consistency of data and determine its limitations | Project | Training benefits and limitations report | M | Hasn't started |  |  |  | Imagery training body |  |  |  | To be carried out by the Benthic Imagery Training Body (Task 10)
Training and Quality Assurance | 75 | Review imagery analysis training approaches for video and stills and identify training needs across UK, identify gaps and scope out training workshops/courses to meet training needs | Project | Imagery analysis training needs Training workshops and courses proposals | H | Hasn't started |  |  |  | Imagery training body |  |  |  | To be carried out by the Benthic Imagery Training Body (Task 10)
Training and Quality Assurance | 76 | Collate all existing training materials, guidance and analysis tools and make centrally available as a common resource | Project | Imagery training resource hub | H | Hasn't started |  |  |  | Imagery training body |  |  |  | To be carried out by the Benthic Imagery Training Body (Task 10)
Training and Quality Assurance | 77 | Create pathways for reference collection imagery, especially from image annotation software, for testing and training purposes | Project | Recommendations for best flows of reference collection imagery for use in ring tests and training | M | Hasn't started |  |  |  | Ring test managing body and Imagery training Body |  |  |  | To be carried out by the Benthic Imagery Training Body (Task 10)
Training and Quality Assurance | 78 | Develop new training courses and materials to meet imagery training needs, along with minimum training requirements (for each course), including materials for specific taxa using expert knowledge (e.g. Seasearch guides) and machine learning courses and support for benthic biologists and ecologists | Multiple projects | Courses and materials bespoke to training needs identified in the review | H | Hasn't started |  |  |  | Imagery training body |  |  |  | To be carried out by the Benthic Imagery Training Body (Task 10)
Training and Quality Assurance | 79 | Develop standard method for assessing differences between datasets determined by different observers as a part of QA | Project | Observer data assessment tool for QA | H | Hasn't started |  |  |  | NMBAQC |  |  |  | Should this be led by NMBAQC?
Training and Quality Assurance | 80 | Assess factors of analyst variability (fatigue/stress/time of day) on imagery and develop recommendations for best practice | Project | Guidelines for annotation best practice | M | Hasn't started |  |  |  | NMBAQC |  |  |  | Should this be led by NMBAQC?
Training and Quality Assurance | 81 | Evaluate analyst variability for quality control purposes to estimate acceptable levels of error | Project | Analyst variability assessment tool for ring tests | M | Hasn't started |  |  |  | NMBAQC |  |  |  | Should this be led by NMBAQC?
Training and Quality Assurance | 82 | Evaluate habitat variability giving examples of specific habitats and species to estimate acceptable levels of error | Project | Guidelines on acceptable levels of habitat and species variability | M | Hasn't started |  |  |  | NMBAQC |  |  |  | Should this be led by NMBAQC?
Training and Quality Assurance | 83 | Review of quality assessment approaches for imagery, including ring tests and NMBAQC recommendations for quality control checks | Project | Updated NMBAQC quality control checking guidelines for internal and contracted work | M | Hasn't started |  |  |  | NMBAQC |  |  |  | Should this be led by NMBAQC?
Training and Quality Assurance | 84 | Develop simple methods to quantify imagery data quality, perhaps using test cards that ask participant which square they can resolve | Project | Image quality assessment tool | M | Hasn't started |  |  |  | NMBAQC |  |  |  | Should this be led by NMBAQC?
Training and Quality Assurance | 85 | Identify and develop a range of quality assurance measures (competency tests?) for different imaging purposes | Multiple projects | Quality assurance measures/competency tests required to meet all standard purposes | M | Hasn't started |  |  |  | NMBAQC |  |  |  | Should this be led by NMBAQC?
Training and Quality Assurance | 86 | Create training standards/accreditation scheme | Project | Training standards/accreditation scheme | M | Hasn't started |  |  |  | NMBAQC |  |  |  | Should this be led by NMBAQC?
Training and Quality Assurance | 87 | Development of an online training module system | Project | Imagery training resource hub: live training module system | L | Hasn't started |  |  |  | NMBAQC |  |  |  | Should this be led by NMBAQC?

## Big_Picture_Group
List of organisations involved in Big Picture Group:
Type of organisation | Organisation
Statutory Nature Conservation Bodies for the UK (note DAERA is also a devolved government department in Northern Ireland) | Joint Nature Conservation Committee (JNCC)
Natural Resources Wales (NRW)
Natural England (NE)
Marine and Fisheries Division, Department of Agriculture, Environment and Rural Affairs (DAERA)
Scottish Natural Heritage (SNH)
Government- and research council-funded research institutes | Agri-Food Biosciences Institute (AFBI)
Biofar (Faroe Islands)
Centre for Environment, Fisheries and Aquaculture Science (CEFAS)
National Oceanography Centre (NOC)
Marine Scotland Science (MSS)
Government-funded environmental protection agencies and fisheries authorities | Eastern Inshore Fisheries and Conservation Authority (IFCA)
Environment Agency (EA)
Scottish Environmental Protection Agency (SEPA)
Independent marine research institutes | Marine Biological Association of the UK (MBA)
Scottish Association for Marine Science (SAMS)
Wageningen Marine Research (Netherlands)
Universities with academic researchers working in various fields of marine benthic imagery analysis | Heriot-Watt University
University of East Anglia
University of Edinburgh
University of Plymouth
University of Southampton
University of Ulster
Environmental consultancies (organisations and independents) | APEM
Aquatic Survey and Monitoring Limited (ASML)
Bureau Waardenburg BV (Netherlands)
Cloudbase Productions
Crangon Limited
Ecospan Environmental Limited
Envision Mapping Limited
Fugro GB Marine Limited
Gardline
Marine EcoSol
Precision Marine Survey Limited
Ocean Ecology Limited
Seastar Survey Limited
Government departments | Department of Agriculture, Environment and Rural Affairs (DAERA)
Department of Environmental, Farming and Rural Affairs (DEFRA)
Marine Scotland (MS)